## Color
PROJECT: Life Planner
LIU |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hiba Shaito-42230627
Project start date: | 2025-02-17 |  |  |  |  | February | [6 empty] | March | [27 empty] | April | [37 empty] | May
Scrolling increment: | 10 | time axis 2025-02-27 to 2025-06-03
Milestone description | Category | Weeks | Progress | Start | Days | time axis 2025-02-27 to 2025-06-03
2025-02-17
Documentation
Project Introduction | On Track |  | 100% | 2025-02-17 | 2
Storyboard Presentation | On Track |  | 100% | 2025-02-19 | 26
Business Process Presentation | On Track |  | 100% | 2025-03-17 | 5
Use Case and ER Diagram Presentation | On Track |  | 100% | 2025-03-22 | 27
Final Documentation | On Track |  | 100% | 2025-04-18 | 42
Firebase Authentication Implementation
Set Up Firebase Project | High Risk |  | 100% | 2025-02-19 | 2
Enable Authentication Methods (e.g., email/password, Google Sign-In) | High Risk |  | 100% | 2025-04-16 | 6
Implement Authentication UI | Low Risk |  | 100% | 2025-04-16 | 3
Test and Secure Authentication Flows | Med Risk |  | 100% | 2025-04-22 | 5
Firestore Database Design and Integration
Set Up Firestore in Firebase Console: | High Risk |  | 100% | 2025-02-19 | 2
Develop Data Interaction Functions: Write functions to add, retrieve, update, and delete data within Firestore. | High Risk |  | 100% | 2025-04-22 | 22
Test Database Operations | On Track |  | 100% | 2025-05-14 | 5
Chatbot Development and Integration
Develop Chatbot Conversational Flow | Med Risk |  | 100% | 2025-05-15 | 2
Integrate Chatbot with Firestore | Low Risk |  | 100% | 2025-05-17 | 1
Implement User Interaction Features | Med Risk |  | 100% | 2025-05-18 | 3
Test Chatbot Functionality | On Track |  | 100% | 2025-05-21 | 1
Application Design and Frontend Development
Develop Frontend Components | Med Risk |  | 100% | 2025-04-22 | 10
Integrate Frontend with Backend | Med Risk |  | 100% | 2025-05-14 | 5
Optimize UI for Performance and Responsiveness | Med Risk |  | 100% | 2025-05-20 | 10
Additional Features Development
Weather Forecast Integration | Low Risk |  | 100% | 2025-05-21 | 1
Daily Quote Display | Low Risk |  | 100% | 2025-05-22 | 1
Test and Refine Additional Features: | Med Risk |  | 100% | 2025-05-23 | 3
Apk creation and testing | Milestone |  | 100% | 2025-05-26 | 2 | bar: 2025-05-26 to 2025-05-27